## Sheet1
S.No | Action Items | Owners | Start Date | End Date | Remarks
1 | SetUp Linux on Rasberry Pi 3 | Saurabh/Adesh | 2017-09-28 |  | Saurabh and Adesh will be working on it
2 | Set Up Jenkins 2.X pipeline on Linux Academy VM | Hitesh |  |  | Push the code in git repostory
3 | ML implementation for Image sensor | Adesh |  |  | Poc to read the image sensor using python
4 | ML implementation for WebCam | Deepak |  |  | Python script to turn on the webcam on any notification
5 | Read the images sensor data poc | Mohsin |  |  | How can we read the sensor data, Kinesis will be expensieve, need any freeware or trial version
6 | Pass the image sensor data to webcam code | Mohsin |  |  | Idea is to turn on the code on any specific event, that event will be captured from image data
7 | Poc to monitor the rasberry pi from any hosted server | Hitesh |  |  | Hitesh for now you cam utilize the linux academy server to trigger the event based from LA vm to rasberry pi
8 | ML implementation for AirPlay | Saurabh |  |  | Poc to create the rasberry pi as Apple TV to sync up with any iphone device. It will help the another poc to integrate the ML with mobile devices
9 | How to integrate the ML code with DevOps |  |  |  | Hitesh and Saurabh will work on set up the jenkins pipeline to triger the different jobs like Image sensor, apple tv, webcam event
10 | Docker implementation | Everyone |  |  | Startegy to build the containers and deploy them on any event produced from above three jobs. Idea is to deploy the different containers for different sensors and run it. Need to dicuss and find the use case for it